## Implementation Checklist
IFRS 18 — IMPLEMENTATION CHECKLIST
Effective 1 January 2027 · Three-phase implementation plan · Retrospective application required
■ Complete | ■ In Progress | ■ Not Started | ■ N/A
# | Task | Owner | Target Date | Status
| PHASE 1 — IMPACT ASSESSMENT |  | 2025 – Early 2026
1 | Map current income statement line items to five IFRS 18 categories (Operating, Investing, Financing, Tax, Discontinued ops). Document classification rationale for any judgement calls. |  |  | Not Started
2 | Assess each associate and joint venture: integral to main business (Subtotal 2) vs non-integral (Investing category). Document basis for each classification. |  |  | Not Started
3 | Identify all Management Performance Measures (MPMs): review last two years of press releases, investor presentations, annual report narratives, and earnings calls. |  |  | Not Started
4 | Model the three mandatory subtotals (Operating profit; + integral associates; before financing and tax) using current period figures. Compare to current reported metrics. |  |  | Not Started
5 | Identify unusual items from recent periods — income/expenses from events clearly distinct from ordinary activities. Assess materiality for separate disclosure. |  |  | Not Started
6 | Assess cash flow statement impact: identify interest paid/received and dividend items currently classified using IAS 7 policy choice. Reclassify under IFRS 18 alignment. |  |  | Not Started
7 | Brief audit committee and board on key changes — particularly the new subtotals and MPM disclosure requirements. Set expectations on what headline metrics will change. |  |  | Not Started
8 | Assess IFRS 19 eligibility for any subsidiaries with separate IFRS reporting requirements. Confirm whether local law permits IFRS 19 use in relevant jurisdiction. |  |  | Not Started
9 | Consider whether financial entities (banks, insurers, finance subsidiaries) within the group require different category treatment for interest income/expense. |  |  | Not Started
| PHASE 2 — DESIGN & SYSTEMS |  | Mid 2026
10 | Redesign chart of accounts or P&L mapping codes to capture the five IFRS 18 categories separately. Ensure ERP system can produce the new required subtotals. |  |  | Not Started
11 | Update ERP or consolidation system configurations to produce IFRS 18-compliant income statement structure with three mandatory subtotals. |  |  | Not Started
12 | Design MPM note disclosure template: reconciliation format, tax effect calculation, NCI effect, explanation of why each MPM provides useful information. |  |  | Not Started
13 | Draft restated FY2025 income statement using new IFRS 18 structure. This will be the comparative period in the first IFRS 18 accounts. |  |  | Not Started
14 | Update accounting policies — add new section defining IFRS 18 category classifications, integral/non-integral associate criteria, and unusual items policy. |  |  | Not Started
15 | Review and rationalise MPMs: consider whether any can be discontinued to reduce disclosure burden. Simplify where investor communication value is low. |  |  | Not Started
16 | Update investor relations materials and brief analysts on coming changes. For entities with significant associate income, model the new subtotals vs current operating profit before external communication. |  |  | Not Started
17 | Engage auditors early on MPM disclosures — MPM note is audited. Agree content and format before accounts preparation. Address any consistency concerns. |  |  | Not Started
18 | If adopting IFRS 19 for subsidiaries: confirm eligibility, obtain legal sign-off for the jurisdiction, review lender/shareholder agreements for full IFRS requirements. |  |  | Not Started
| PHASE 3 — PARALLEL RUN & FIRST REPORTING |  | 2026 – 2027
19 | Run IFRS 18 income statement in parallel from Q1 2026 (or first interim period). This allows system issues and classification judgements to be resolved before statutory accounts. |  |  | Not Started
20 | Resolve all outstanding classification judgements. Document rationale for each. Ensure consistent treatment across all entities in the group. |  |  | Not Started
21 | Finalise and agree MPM disclosures with auditors. Ensure all public communications in 2026 are consistent with the IFRS 18 MPM definitions being adopted. |  |  | Not Started
22 | Prepare final FY2026 restated comparatives ready before first 2027 interim report. Ensure restatement covers all entities in the consolidation. |  |  | Not Started
23 | For half-year or quarterly reporters: plan first IFRS 18 P&L disclosure in interim report. Brief investors and analysts before first publication of new format. |  |  | Not Started
24 | Prepare investor/analyst communication explaining new income statement structure, new subtotals, and any changes to MPM calculations or definitions. |  |  | Not Started
25 | First year of application: include required disclosure of adoption of IFRS 18 in significant accounting policies. Confirm no practical expedients used (or disclose which). |  |  | Not Started
26 | Post-implementation review: after first IFRS 18 accounts, assess whether MPM disclosures are working as intended and whether any further rationalisation is appropriate. |  |  | Not Started
PROGRESS SUMMARY
Total tasks
Complete
In Progress
Not Started